## Journal de travail
Journal de travail
| Auteur: | Ethan Schafstall |  | Projet: | P_I183 | Analyse | Dévelopement | Test | Documentation | Meeting
| Temps total: | 9:30 | heures | Date: | 2024-03-22
Semaine | Jour | Temps [h] | Type | Description | Remarques/problèmes
12 | 2024-03-22 | 0.010417 | Meeting | Finished project introduction and specifications discussion.
12 | 2024-03-22 | 0.010417 | Documentation | Set up project environment & tools | Downloaded and installed vscode & vscode plugins, github desktop.
12 | 2024-03-22 | 0.010417 | Documentation | Set up base project documents. | Project report, work journal.
12 | 2024-03-22 | 0.010417 | Analyse | Creation of the web application schema/diagram. | First version on paper.
12 | 2024-03-22 | 0.010417 | Analyse | Search on connecting the api to the database, and querying without sequelize. | First version on paper.
12 | 2024-03-22 | 0.010417 | Analyse | Research on mysql npm package && how to update docker containers with packages.
12 | 2024-03-22 | 0.010417 | Test | Testing mysql package and connection to the db | Started testing, connection keeps failing
12 | 2024-03-22 | 0.010417 | Documentation | Testing mysql. Updated JNLTRAV && commiting base files/folders to github repo. | Wasn't able to connect to DB using mysql package
16 | 2024-04-19 | 0.010417 | Analyse | Reading offical mysql2 node documentation | Making sure I fully understand how to use it.
16 | 2024-04-19 | 0.010417 | Dévelopement | Implimentation of the mysql2 package
16 | 2024-04-19 | 0.010417 | Test | Tests (connection to db, queries, inserts) | Fully working
16 | 2024-04-19 |  | Analyse | Analysing api schema
16 | 2024-04-19 |  | Analyse | Research on sql injection
16 | 2024-04-19 |  | Analyse | Research on sql injection
16 | 2024-04-19 |  | Test | Testing the newly created modules
16 | 2024-04-19 |  | Dévelopement | Fixing bugs with how the modules interact with each other/refract
16 | 2024-04-19 |  | Documentation | Filled out JNLTRAV
17 | 2024-04-26 | 0:15 | Analyse
17 | 2024-04-26 | 0:15 | Analyse
17 | 2024-04-26 | 0:15 | Dévelopement
17 | 2024-04-26 | 0:15 | Dévelopement
17 | 2024-04-26 | 0:15 | Dévelopement
17 | 2024-04-26 | 0:15 | Dévelopement
17 | 2024-04-26 | 0:15 | Dévelopement
17 | 2024-04-26 | 0:15 | Dévelopement
17 | 2024-04-26 | 0:15 |  | Helped Lucas with a token error
18 | 2024-05-03 | 2:15 |  | ABSENT
20 | 2024-05-17 | 2:15 |  | ABSENT
Formulas:
Semaine = IF(ISBLANK([Auteur:]),"",ISOWEEKNUM(Table2[[#This Row],[Jour]]))